## Plan
Task | Owner | Status | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19
Planning meeting | Richard | Open
Technical design meeting | Richard | Open
Schenker development of extraction process | Schenker | Open
Intermec setup of BizTalk FTP accounts | Richard | Open
Test extraction process in development systems and resolve issues | Richard/Schenker | Open
Test extraction process in test systems and resolve issues | Richard/Schenker | Open
Train users on business process for report | Cecilia | Open
Move development to production system | Richard/Schenker | Open

## Agreements
Inventory Reconciliation Requirements | Meeting Result | Status
Intermec SAP is the system that runs the comparison and drives the formatting requirement for the file to be imported. |  | Open
IT staff for both systems agree to a “quiet” time during the day where both Intermec SAP and Schneker system have no transactions occurring for Schenker Singapore inventories. This is so no inventory transaction occur after extraction from Schenker system, but before process in Intermec SAP system, which would result in an incorrectly reported discrepancy. |  | Open
IT staff for both systems agree to frequency for which the inventory reconciliation process will occur. Standard approach is to have the process occur once per day, 7 days a week. |  | Open
The Schenker IT Staff agrees to conversion of their system location and status data into SAP formatted location and status data per the INventory Recon function spec document. Example conversion: Schenker system location C1001, available status maps to Intermec SAP system location and status of 0020 UNRES. |  | Open
IT staff for both systems agree to a location on where to save the extraction file. |  | Open
Schenker IT staff agree to extract the file per Intermec specifications of either a .TXT or XML file and place that file out to the supplied Intermec FTP site. FTP account and password data to be setup and provided by Intermec to Schenker. |  | Open
Schenker and Intermec business teams agree to a business process where Schenker users access the report and troubleshoot inventory discrepancies with assistance from designated Intermec person as needed. |  | Open