## Minutes
Request | WMS RF Expiry capture and inventory matching with SAP Inventory
Date | 2014-10-28
Attendee | Ops: Yeo Wei Khoon David Lim Cheang KH Tan IT: Henry Tjan, Pei Fong
Objective | to review current expiry capture process in WMS and solution to get the expiry inventory balance status matching with SAP inventory.
Issues | 1. The Initial Expiry item matching with SAP inventory was design by matching SAP TO Quant (Inbound Putaway) and SKU, however the TO quant will always get updated for each product transfer, pick or moved. Hence, WMS system will not able to match the Expiry by TO Quant.
Propose solution | 1. Expiry inventory in WMS to match by summary of Part# + Location + TotalQtyAvailable against SAP Inventory Report. 2. GR# decided not to capture in WMS, because it's not available on the putaway label and not able to retrieve such matching of TO# Vs GR# report in SAP report. 3. . WMS system will base on Balance quantity downloaded (StockAvailable) in SAP report to perform inventory StockOut in WMS Expiry inventory by First Expiry First Out logic (FEFO) upon every new inventory import into WMS. Scenario example for the inventory matching: WMS Expiry: Line SKU LOC Qty ExpiryDate 1 ABC A 2 6/15 2 ABC A 3 8/15 3 ABC A 3 9/16 SAP Report: Date, SKU LOC QTY 1/10 ABC A 8 -> system match in WMS locA total qty = 8, no action in WMS 2/10 ABC A 7 -> system stock out Loc A (line1) which expirydate = 6/15, from qty 2- 1 = 1 , WMS LOC A , total qty = 7 3/10 ABC A 6 -> system stock out Loc A (line1) which expirydate = 6/15, to qty = 0, WMS Loc A, total qty = 6 ABC B 1 -> system not match found.
REPORTS: Date: 1/10 Line SKU LOC Qty ExpiryDate Status 1 ABC A 2 6/15 OK 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK Date: 2/10 Line SKU LOC Qty ExpiryDate Status 1 ABC A 1 6/15 OK 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK Date: 3/10 Line SKU LOC Qty ExpiryDate Status 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK 4 ABC B 1 NotMatch

## Changes
IT Changes Task List
S/N | Module | Description | Priority (Phase) | Manday | Start Date | Target Date | Status | Actual Completed date | UAT
1 | RF Capture Expiry | To add Qty input TO Quant remain during scanning to serve as prevention of duplicate scanning of expiry data capture. |  | 3 | 2014-10-29 | 2014-10-31
2 | Inventory Matching Report | New inventory report to show inventory status by matching SKU+LOC+Qty |  | 3 | 2014-11-03 | 2014-11-07
3 | Expiry Inventory auto stockout adjustment | after new snapshot of inventory updated, system process matching and adjust the new inventory balance in WMS based on SAP Report by grouping by SKU+LOC + SubTotalQty |  | 3 | 2014-11-10 | 2014-11-13
4 | Transfer Loc | Screen to allow user to transfer WMS expiry Location |  | 2 | 2014-11-18 | 2014-11-20
QTY