## Minutes
Request | WMS RF Expiry capture and inventory matching with SAP Inventory
Date | 2014-10-28
Attendee | Ops: Yeo Wei Khoon David Lim Cheang KH Tan IT: Henry Tjan, Pei Fong
Objective | to review current expiry capture process in WMS and solution to get the expiry inventory balance status matching with SAP inventory.
Issues | 1. The Initial Expiry item matching with SAP inventory was design by matching SAP TO Quant (Inbound Putaway) and SKU, however the TO quant will always get updated for each product transfer, pick or moved. Hence, WMS system will not able to match the Expiry by TO Quant.
Propose solution | 1. Expiry inventory in WMS to match by summary of Part# + Location + TotalQtyAvailable against SAP Inventory Report. 2. GR# decided not to capture in WMS, because it's not available on the putaway label and not able to retrieve such matching of TO# Vs GR# report in SAP report. 3. . WMS system will base on Balance quantity downloaded (StockAvailable) in SAP report to perform inventory StockOut in WMS Expiry inventory by First Expiry First Out logic (FEFO) upon every new inventory import into WMS. Scenario example for the inventory matching: WMS Expiry: Line SKU LOC Qty ExpiryDate 1 ABC A 2 6/15 2 ABC A 3 8/15 3 ABC A 3 9/16 SAP Report: Date, SKU LOC QTY 1/10 ABC A 8 -> system match in WMS locA total qty = 8, no action in WMS 2/10 ABC A 7 -> system stock out Loc A (line1) which expirydate = 6/15, from qty 2- 1 = 1 , WMS LOC A , total qty = 7 3/10 ABC A 6 -> system stock out Loc A (line1) which expirydate = 6/15, to qty = 0, WMS Loc A, total qty = 6 ABC B 1 -> system not match found.
REPORTS: Date: 1/10 Line SKU LOC Qty ExpiryDate Status 1 ABC A 2 6/15 OK 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK Date: 2/10 Line SKU LOC Qty ExpiryDate Status 1 ABC A 1 6/15 OK 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK Date: 3/10 Line SKU LOC Qty ExpiryDate Status 2 ABC A 3 8/15 OK 3 ABC A 3 9/16 OK 4 ABC B 1 NotMatch
SUMMARY: @10/11/2014 | To recap: New logic=> the Expiry date matching report will be based on SAP Material Code + Storage location + total SAP QtyAvailable match against WMS Scanned Expiry item data. 1. Expiry Inventory Status reports (ver 2) - READY This report will provide 2 section of inventory status a. Inventory balance matching status – refer “System Match Status” – result of the comparing inventory in SAP ( SKU+StorageBin ) vs WMS i. WMS Matched = SAP SKU+Location and balance qty vs WMS is matched ii. WMS Qty not match = SAP SKU+Location matched WMS but balance qty not match. (This stock will continue keep in WMS, until all the qty depleted in SAP ) iii. Not in SAP = WMS Scanned data not found in SAP (this line will auto-stock out, when SKU+Location in WMS but not found SAP inventory) iv. WMS Not Update = SAP SKU+Location not found in WMS - > Team need to update the Expiry Date in WMS b. Item expiry status detail “Expiry Status” – result of the expiry status i. EXPIRED – item with month-to expiry less than 4 months ii. ALERT – item with month-to expiry = 5 months iii. NORMAL – item with month-to expiry greater than 4 months iv. NOT UPDATE – item not in WMS expiry scan detail 2. Expired List report – List of expired item in WMS. the report format will be same as Expiry Inventory report - READY 3. Daily Scanned detail report – List of daily scanned Expiry date item, Storage type = “NA” refer to the item is not available in SAP Inventory Report. - READY

## Changes
IT Changes Task List
S/N | Module | Description | Priority (Phase) | Manday | Start Date | Target Date | Status | Actual Completed date | UAT
1 | RF Capture Expiry | To add Qty input TO Quant remain during scanning to serve as prevention of duplicate scanning of expiry data capture. | 1 | 3 | 2014-10-29 | 2014-10-31 | DONE | 2014-10-30 | 2014-11-06
2 | Inventory Matching Report | New inventory balance report to show inventory status by matching SKU+LOC+Qty [WMS] -> [Expiry] -> Expiry balance base on SAP Inventory balance matching WMS by groupin gof SKU and Location Report provide matching status : 1. WMS Matched 2. WMS Qty not match 3. Not in SAP 4. WMS Not Update | 1 | 3 | 2014-11-03 | 2014-11-07 | Done | 2014-11-06 | 2014-11-06
3 | Expiry Inventory auto stockout adjustment | after new snapshot of inventory updated, system process matching and adjust the new inventory balance in WMS based on SAP Report by grouping by SKU+LOC + SubTotalQty [06/11] stay quote, ops still settling issue Scanned in WMS but not valid in SAP system. [13/11] ops put-away cut-off time @23:00 in SAP system, SAP inventory report will be download into WMS. WMS will zero stock out item that has no inventory available in SAP raw file. | 1 | 3 | 2014-11-10 | 2014-11-13 | DONE | 2014-11-13 | 2014-11-14
4 | RF Transfer Loc Move Expiry | Screen to allow user to transfer WMS expiry Location | 1 | 2 | 2014-11-18 | 2014-11-20 | DONE | 2014-10-31 | 2014-11-01
5 | Inventory Status report | New report version 1. Expiry Inventory Status reports (ver 2) This report will provide 2 section of inventory status a. Inventory balance matching status – refer “System Match Status” – result of the comparing inventory in SAP ( SKU+StorageBin ) vs WMS i. WMS Matched = SAP SKU+Location and balance qty vs WMS is matched ii. WMS Qty not match = SAP SKU+Location matched WMS but balance qty not match. (the auto-stock out will kick in into system at later date) iii. Not in SAP = WMS Scanned data not found in SAP (this line will auto-stock out, when SKU+Location in WMS but not found SAP inventory) iv. WMS Not Update = SAP SKU+Location not found in WMS b. Item expiry status detail “Expiry Status” – result of the expiry status i. EXPIRED – item with month-to expiry less than 4 months ii. ALERT – item with month-to expiry = 5 months iii. NORMAL – item with month-to expiry greater than 4 months iv. NOT UPDATE – item not in WMS expiry scan detail |  | 2 | 2014-11-03 | 2014-11-05 | DONE | 2014-11-14 | 2014-11-14
6 | Expired List | Created Expired List report – List of expired item in WMS. the report format will be same as Expiry Inventory report |  | 1 | 2014-11-03 | 2014-11-05 | DONE | 2014-11-01 | 2014-11-01
7 | Daily Scanned Detail Report | 3. Daily Scanned detail report – List of daily scanned Expiry date item, Storage type = “NA” refer to the item is not available in SAP Inventory Report. Added SAP QtyAvail, WMS qty Avail, matching status ( Valid in SAP or Not in SAP) - User to validate daily on the scanned expiry vs SAP system. may have item scanned but not Putaway Confirm in SAP. |  | 1 | 2014-11-03 | 2014-11-05 | DONE | 2014-11-01 | 2014-11-01
QTY