## Process Diagram
Proposed: | Revised version dated 24 Jul 2014 | Option 1 | Inbound storekeeper to input Carton detail at the same time when measuring weight/Dim.
|  | Option 2 | To split the Measuring and input of Carton detail into 2 individual process.
Inbound Storekeeper weight/Dim measure using CargoSCan.
And concurrently another user can use RF scanner to input Carton LP detail

## IT Task
Task# | Module | Detail description | Option 1 Manday | Option 2 Manday | Task Assign to | Status (progress -%) | Date start | Dev. Date completed | Date UAT | Remarks
1 | Interface-CargoScan | interface to capture data capture from CargoScan machine to WMS new screen - LP attributes Data capture: LP (BoxID) , Dimension (L,W,H in cm) and weight (kg) data will be capture in new data table : LPAttributes Option: FTP or TCP direct | 5 | 6 | Daniel |  |  |  |  | [16/05/2014] prototype done, waiting physical cargoscan machine for integration testing
2 | WMS-CargoScan Screen | new LP attribute (AutoScanData) capture screen: LP: Scan Dimension: L x W x H { auto from CargoScan} Weight: kg { auto from CargoScan} Carton Qty: {User input} COO : {user input} Received Date : ( system default to current) | 3 | 0 | Daniel
3 | WMS-RF Putaway (new) | to allow 'dummy' putaway for pre-scanned Box using CargoScan | 2 | 2 | Daniel
4 | Inbound Creation | add column expected total Box in ASN Line, new pop out screen to scan in matches LPs # per ASN Line | 2 | 2 | Daniel
5 | ASN Auto finalised | System will auto look up the respective Dimension, weight, coo , carton qty and received date from LP Attributes AutoScan Data for receiving. LP actual receiving date will be based on the ScanCargo- LP Attributes' ReceivedDate. Auto finalise to have functions: 1. auto received per LP 2. Verify STGC Move 3. Verify Total Qty Per ASN Line ( using existing Receipt Report ) 4. Verify Total LP per ASN Line ( to add into Receipt Report) | 3 | 5 | Daniel
6 | STGC Putaway List | Generate list of outstanding put-away STGC SKU list | 1 | 1 | Daniel
7 | Print LP Info label or Report screen | Scan LP to auto generate label or LP Work sheet. Condition: if total received LP >= 2 LPs, system print out LP Work Sheet, if total received LP < 2 LPs , system print label. Label : Dimension and weight and qty Worksheet: (format follow current Inbound worksheet) Part#, IBMPO#, LP, Dimension, weight and qty Label size: Height: 1.5 CM Width: 4.5 CM | 2 | 2 | Daniel
8 | STC Storage billing | to verify the Storage incoming date to be based on the LP Attributes Received Date - change storage billing to calculate based on Lotattribute.Lottable05 | 1 | 1 | PF
9 | Outstanding and exception report | List of outstanding LP and exception report for LP that is not finalise receive. | 2 | 2 | PF
9 | Option 2 - RF WMS-CargoScan Input | Input new LP attribute (AutoScanData) via RF LP: Scan Dimension: L x W x H { auto from CargoScan} Weight: kg { auto from CargoScan} Carton Qty: {User input} COO : {user input} Received Date : ( system default to current) | 0 | 5
|  |  | 21 | 26
Note on D1: Author: selected Option 1 > Inbound Measure and input carton detail at the same time.

## Interface with Vendor
Interface solution | A brief Proposed interface plan and some questions for the vendor for Cargo Scan base on cargoscan specs. 1. Cargo Scan to be the TCP Socket Server (1.1.1) - TCP port - 8000 (or the default/current value being used by airfreight) 2. Wms as tcp client - TPC port 8000 (or the default/current value being used by airfreight will be configurable in wms.ini) 3. i guess the Format ( base on specs 1.1.2) can be set to default values for the time being or use the current config being use by airfreight. Dim : Centimeters and Kilograms 4. Field Editor (1.1.4) for the time being can also be left at the current config as being used by airfreight. 5. Heartbeat can be send every second or so as this can also be a visual aid for the user/operator by color animation in wms. Heartbeat message HBT\r\n | 2014-05-16
Questions to vendor: | Questions to vendor: a. We noticed that there is an optional checksum that can be send in message/packet, but there is no acknowledgement/nack protocol in place. what if we use this function and in the receiving end (which is wms) receive the message and when re-computes the checksum is different, how should this be handled? [MT] There is an acknowledgement function. Please refer to the attached document, do a search on 'acknowledgement' (page 101, 102). Is this what you need? b. Error Code, Dim Error, dim status (1.1.4). How to handle error code? in the specs zero indicates a good result, what if the value is not zero? should we discard the whole message and re scan the package? same question for scale error and scale status. c. [MT] There are settings on Octo software. (see page 58 of attached) if you use 'Simple manual accept': when there is a failed measurement (too big, too small, out of position), the operator will get a message to allow to enter values manually or re measure the item. Until the measurement is correct, either with manual entry or dimensioner capture', the datastring will then be sent to the host. If you use 'Automatic for all results' , all results (data string) will be sent to host regardless if it is a good measurement or failed measurement. You can configure the data string to indicate 'Error Status', where a non-zero value indicates an error. d. for offline storage, when the connectivity is lost, cargoscan will store the data into a its local disk (1.1.1.4). The question is on the max age field, does this means that when the max age has not been reach will cargo scan re-send the packet when the connectivity is back? same question with max records. [MT] When you reach the limits set OCTO will delete the oldest records in the storage. If max age is reached, Octo will delete the oldest record. So you can set the max age as a huge number, limitation is based on hard disk size which I believe will not be a problem even if it’s storage for days of records | 2014-05-16
CargoScan Measure Acceptance mode setting | there are a few modes to choose from. Refer to the following, or page 50 of the attached manual. To ensure that the operator is alerted with the 'error message/reason' when measuring fails, and does a remeasure… you can use the mode in red (below) Manual entry of dimensions and weight (when measuring fails), can be either disabled or enabled during setup. Accept mode Specifies how the system software handles data acceptance by operator. • Manually for all results. Operator has to accept all measuring results no matter if measuring was successful or failed. No data is sent to host before data is manually accepted • Automatic for good results. Data is accepted automatically when measuring was successful. If measuring fails then message "Measuring failed" is displayed and then Confirm button brings up screen with more detailed result. One more time "Confirm" stores data. Cancel button drops all measurements and brings back to initial screen. "Remeasure" button starts measuring again with same Parcel Id. • Automatic for all results. All results are automatically accepted without operator intervention. If one or more devices fails on measuring then such data may not be available for host or set to zero, depending situation and error type. • Simple manual accept when failed. Mostly used option. Detailed results and reason for failure are displayed when there was an error. Allows accepting with simple "Confirm" button when measuring fails or discarding results with "Cancel" button. "Remeasure"button is available as well. Good measurements are automatically accepted in this mode.
FTP configurable setting | data transmission can be configured to a specific interval or immediately after measurement, or with thredhold
Transmission string | string message format is flexible to configure using CargoScan app.