## Request
| REQUEST: |  |  | TEST Server | SIN-TEST2008
| Date: 9 Jun 2015 |  |  | DB | SCHTS_VW_NADC
| To have Standard Exceed WMS capability in current VW outbound application to handle packaging material inventory tracking. |  |  | Test ID | vwn.test | 123456
| System Requirement: | Date request | Date Complete | Mandays
1 | Require to migrate current VW database ( do not have exceed WMS capability) into Exceed WMS DB. | 2015-06-15
2 | Prepare test environment for Testing – Migrate VW data into new Exceed WMS DB. – 2015.06.18 | 2015-06-16 |  | 8
- VW DB migration to new Exceed DB
- Recompile Kodigo WMS
- Create Kodigo Application profile
3 | Prepare user testing. – 2015.06.19 to 2015.06.26
4 | Setup - Upload Packaging Material Master and field mapping to SKU | 2015-06-19 | 2015-06-29 | 2
5 | New screen - SAP Packaging material upload function | 2015-06-19 | 2015-06-29 | 3
6 | New Report - Packaging material summary report - inbound balance report | 2015-06-19 | 2015-06-29 | 3
7 | RF Receiving | 2015-07-02 | 2015-07-06 | 3
8 | RF Move | 2015-07-06 | 2015-07-08 | 2
9 | Day-end wms process - inventory snapshot (DailyItrn) to capture daily/weekly movement | 2015-06-29 | 2015-07-01 | 2
23
UAT | 1 - Jul 2015 to 21 Jul 2015
System cut-off | 26-Jul-2015 7pm - 27 Jul 2015 8AM inventory migration. | 2015-07-26 | 2015-07-27 | 1
Go-Live | 2015-07-28 | 2015-07-28 | 2015-07-28
Post Live | Packaging inventory migration cut-off 30-Jul migration to Live WMS | 2015-07-31 | 2015-07-31 | 1
NEW WMS DB: | SCHPR_VW_NADC
Server | Sin-WRANGLER16
Preparation prio Go-LIVE:
Please be inform that we will go “Live” on the Packaging Material In & Out thru WMS with Effect from 28-Jul-2015. Please follow accordingly to the below timeline and I will transfer the Testing Inventory to “live” system.
1. All system testing of the In & Out cut “OFF” on 22-Jul-2015 4pm.
2. IT will clear all the Inventories in the “Test” System by 5pm on 22-Jul-2015.
3. Packaging Material In-Charge will perform the Receiving using the “Pallet ID” which I printed previously, latest by 26-Jul-2015 6pm.
4. IT will transfer the Packaging Material “Inventories” to the “Live” system on the 27-Jul-2015 Morning.
5. System will resume on the 28-Jul-2015 morning.
Team, if possible try to complete Receive by 24-Jul-2015 3pm , so that we can generate from WMS and send to VW.

## WMS Module
Module | Function | Description
Master | SKU Maintenance | Maintain SKU master
Master | Locaiton Maintenance | Maintain Location master
Master | Forwarder Maintenance | Maintain Forwarder Master - for outbound
Master | Packkey Maintenance | Sku packkey setup
Inbound WMS | ASN Creation | Create and Maintain Inbound ASN
Inbound WMS | Inbound Tally Sheet | Print Inbound tally sheet (ITS)
Inbound WMS | Receiving | Perform inbound receiving by ASN#
Inbound WMS | Pending Putaway | Report for Pending putaway list
Inbound WMS | Receipt Confirmation Report | Confirmation receipt by ASN
Outbound WMS | Order Creation | Create orders
Outbound WMS | Order Allocation/Ship | Perform Order allocation , pick , ship
Outbound WMS | Pick Ticket | Print Picking list
Outbound WMS | Packing Entry | process Packing by ship-to
Outbound WMS | Stock out report | Outbound Stock out report by orders
Inventory | Inventory Balance | view inventory balance
Inventory | Inventory Move | Perform inventory move
Inventory | Inventory Adjustment | Perform inventory adjustment
Inventory | Inventory Transaction | view inventory transaction history
Inventory | Inventory Transfer | Perform inventory transfer
Inventory | Inventory Attributes | Allow user to update inventory lot attributes
Cycle Count | Location Format maintenance | setup location format
Cycle Count | Cycle count entry | Generate cycle count
Cycle Count | Cycle count report | print cycle count report
Report WMS | WIP Report | Work in progress
Report WMS | Daily Receiving Report | Retrieve Daily Receiving Report by received date range
Report WMS | Daily Outgoing report | Daily Outgoing report by shipped date range
Report WMS | Aiging Report | Aiging Report
Report WMS | Shelf life Report | Shelf life Report
Report WMS | 3 in 1 report | 3 in 1 report - transaction history report
Report WMS | Inventory Balance Report | Inventory Balance Report
Report WMS | Inventory Adjustment Report | Inventory Adjustment Report
Report WMS | Inventory Transfer Report | Inventory Transfer Report