## Sheet1
Date | 2015-10-26
Agenda | SKH-OFI new requirements
Attendent | Liew Fong Fong | David LimGH
| Kwek Eng Ho | Marcus Tong | Lee Kok Meng
Pei Fong Chan
Agenda | Discuss OFI requirement - Offload and Rebag
Detail Changes
1 | Offload shipment scanning - Another type of orders. no specific requirement by customer. no system changes. We will be configure the current Wafer Sales scanning function to cater for this OFFLOAD shipment OFI. Action required: a. Create new customer matrix “OFFLOAD” to cater 2 labels scanning validation - HWS vs Box label b. Micron will send OFFLOAD Shipment files to Schenker to import into WMS OFI – using current [WaferSO Import] function. c. Perform OFI Scanning using “OFI -Scanning PACKING”
2 | Rebag scanning – NEW system requirement Rebag process will conduct in clean room; the rebag is to replace the damage packaging received during inbound. Ops will paste new label on the replacement bag. During OFI scan, Ops will scan the original label and new label to ensure the pasting of label is correct. No customer specific requirement for this. The Scanning validation process will be same as outbound OFI scan. a. Develop new import Function for REBAG file import b. Micron will send rebag file to Schenker to import into WMS-OFI c. Develop new REBAG Scanning function to validate 2 labels – Source Label and New Product transfer Label Rebag scanning process will be generic for all customers. d. Develop Rebag Daily scanning report to
3 | 3. Subcon- no system changes. Product Transfer vs box label ( current available function)