## Sheet1
| migration IBMPDL to IBMMSPL ( IBM Manufacturing Solutions Pte. Ltd) |  | Effective 02 Nov 2015
No. | Task Detail | Status | Date completed | Remarks
1 | Master setup SQL: 00_insert Storer.sql - Create storer, SKU | DONE | 31-0ct-2015 | Storer = IBMMSPL
2 | Pre-migration: Validate no outstanding orders | DONE | 31-0ct-2015 | select * from pickdetail where storerkey = 'IBMPDL' and status <> '9'
3 | Transfer Stock: SQL: 01_Tranfer IBMPDL.sql – to Transfer stock - update ReceiptDetail.storerkey to New Storerkey | DONE | 31-0ct-2015 | using ds : ds_transferdetail_import - total 46 LP
4 | Create new storage billing for New storer After stock transferred to new storer, insert billing openning stock balance for new storer IBMMSPL SCH_IBM_Daily_Billing_Storage_Calc_STC_bydate.sql | DONE | 31-0ct-2015 | select * from SCH_IBM_Daily_Billing_Storage where storerkey = 'IBMMSPL' order by 1
5 | SQL Scripts deployment: Inventory reports: SCH_IBMSTC_HUB_Report_Inventory_byIDDN_IBMPO_Report.sql SCH_IBMSTC_HUB_Report_Inventory_Report.sql sp_04_SCH_IBMSTC_LiveReport_Inventory_Report.sql sp_05_SCH_IBMSTC_LiveReport_Inventory_Aging_Report.sql sp_06_SCH_IBMSTC_LiveReport_Inventory_Exception_Report.sql | DONE | 31-0ct-2015
6 | HUB Deployment: ibm_setup.pbd ibm_cyclecount.pbd ibm_report.pbd ibm_outbound.pbd ibm_inbound.pbd | DONE | 31-0ct-2015 | Deployed to SIN-VIS18
7 | Live Report - change the main report folder name . Change 'STC' to 'OSC' | DONE | 31-0ct-2015
8 | Live Reports - change Parameter storerkey from IBMPDL to IBMMSPL | DONE | 31-0ct-2015 | 6 reports - redeployed to Live report server
Snapshot | create SQL JOB - run snapshot IBMMSPL exec SCH_IBM_Inventory_Snapshot_SP 'IBMMSPL' | DONE | 31-0ct-2015
BillingSP | Add Storer IBMMSPL dbo.SCH_IBM_Daily_Billing_Storage_CalcSTC_Main | DONE | 31-0ct-2015