## Summary TimeLine
Activity | Day | Target Date of Completion | Status | Remark
Requirement gathering- process mapping | 1 | 13th Oct 2015
System Design | 1 | 19th Oct 2015
System Development | 11 | 23th Oct - 11th Nov 2015 |  | other project start: 20 - 23 Oct
User (UAT) Testing | 6 | 11th Nov - 18th Nov 2015
System Review fine tuning (if Any) | 4 | 18th Nov - 24 th Nov 2015
Installation (RF/Application)
System Preparation Go-live | 1 | End Nov 2015
24

## Minutes
Date | 13 th Oct 2015 2 PM-5 PM
Meeting: | Dicussion on new outbound loading process - print gatepass | Attendants:
Objective | Corrective action to cater issues: 1. Gatepass was not printed when release container, 2. Container was sealed when truck out - guard house responsibility to visual check on the sealing. Finding: Possible process gap, operation pre-print gatepass before container was sealed or operation cut the sealed container and forget to re-seal container. | KH Tan David Lim Yeo Wei Khoon Ming Fong Cheang Choo (Jacky) | Pei Fong
To-be-process | **<new process flow>
1 | Enter Seal# . (RF) Current: Seal# is enter during pre-loading before physical sealing. To-Be: a> Seal # to be enter after physical sealling, then perform print gatepass (Actual gatepass) b> Seal# entering date/time should be at least 45 mins after Loading scanning. ( loading time for 1 container is about 45 mins) c> For container require treatments, the seal# should be entered after Ventilation completed.
2 | Function [Loading Do - Gatepass] (Current WMS) - the DO print out will always printed as "Draft copy, - printing from RF also set as "Draft copy"
3 | Print GatePass (NEW) -WMS (applicable to all Shipment modes) a> New screen to print gate pass, separating by Warehouse/Site ( = similar to the current Inbound-Container print gatepass (empty truck out) b> system perform validation of HU load completeness by Shipment# and Warehouse ( TLC/SLC) . Do not allow print gatepass if loading has not completed by Shipment#+warehouse. Exception: a> system will allow exception printing gatepass for truck out partial completed shipment #, this will required supervisor authorization. System will prompt incompleted loading of the Shipment#.
4 | Re-print Gatepass (New) - WMS a> Re-entering Seal# is require before allow re-printing of gatepass. System flag out the container has re-entered seal# for re-printing. b> Re-printing gatepass to be done in WMS.
5 | E-Tracker- Add Print gatePass milestone by container. New fields to be added to Alert report. Add new interface to update print gate pass timestamp to e-Tracker from WMS.

## Task list
| Summary IT Requirement - VW Print gatepass control process |  |  |  |  | Updated 2015.10.14
S/N | Module | Function | Detail Description | Manday | By | Start Date | Estimated | Completed Date | SIT | UAT | STATUS | Remarks
1 | RF | Enter Seal# . (RF) | Enter Seal# . (RF) Current: Sela# is enter during pre-loading before physical sealing. To-Be: a> Seal # to be enter after physical sealling, then perform print gatepass (Actual gatepass) b> Seal# entering date/time should be at least 45 mins after Loading scanning. ( loading time for 1 container is about 45 mins) c> For container require treatments, the seal# should be entered after Ventilation completed. | 2
2 | WMS | [Loading Do - Gatepass] | Function [Loading Do - Gatepass] (Current WMS) - the DO print out will always printed as "Draft copy, - printing from RF also set as "Draft copy" | 1
3 | WMS | Print GatePass by warehouse | Print GatePass (NEW) -WMS (applicable to all Shipment modes) a> New screen to print gate pass, separating by Warehouse/Site ( = similar to the current Inbound-Container print gatepass (empty truck out) b> system perform validation of HU load completeness by Shipment# and Warehouse ( TLC/SLC) . Do not allow print gatepass if loading has not completed by Shipment#+warehouse. Exception: a> system will allow exception printing gatepass for truck out partial completed shipment #, this will required supervisor authorization. System will prompt incompleted loading of the Shipment#. | 4
4 | WMS | Re-print gatepass | Re-print Gatepass (New) - WMS a> Re-entering Seal# is require before allow re-printing of gatepass. System flag out the container has re-entered seal# for re-printing. b> Re-printing gatepass to be done in WMS. | 2
5 | e-tracker | Container information | E-Tracker- Add Print GatePass milestone by container. New fields to be added to Alert report. Add new interface to update the milestone to e-tracker from WMS. | 2
6
7
8
9
11

## Sheet1
PROJECT | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-10-31 | 2015-11-01 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29 | 2015-11-30 | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10 | 2015-12-11 | 2015-12-12 | 2015-12-13 | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-19 | 2015-12-20 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25 | 2015-12-26 | 2015-12-27 | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | 2016-01-01 | 2016-01-02 | 2016-01-03 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08 | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-24 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12 | 2016-02-13 | 2016-02-14 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27 | 2016-02-28 | 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-05 | 2016-03-06 | 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-16 | 2016-04-17 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-23 | 2016-04-24 | 2016-04-25 | 2016-04-26 | 2013-03-01 | 2013-03-02 | 2013-03-03 | 2013-03-04 | 2013-03-05 | 2013-03-06 | 2013-03-07 | 2013-03-08 | 2013-03-09 | 2013-03-10 | 2013-03-11 | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2013-03-16 | 2013-03-17 | 2013-03-18 | 2013-03-19 | 2013-03-20 | 2013-03-21 | 2013-03-22 | 2013-03-23 | 2013-03-24 | 2013-03-25 | 2013-03-26 | 2013-03-27 | 2013-03-28 | 2013-03-29 | 2013-03-30 | 2013-03-31 | 2013-04-01 | 2013-04-02 | 2013-04-03 | 2013-04-04 | 2013-04-05 | 2013-04-06 | 2013-04-07 | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-04-14 | 2013-04-15 | 2013-04-16 | 2013-04-17 | 2013-04-18 | 2013-04-19 | 2013-04-20 | 2013-04-21 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-26 | 2013-04-27 | 2013-04-28 | 2013-04-29 | 2013-04-30 | 2013-05-01 | 2013-05-02 | 2013-05-03 | 2013-05-04 | 2013-05-05 | 2013-05-06 | 2013-05-07 | 2013-05-08 | 2013-05-09 | 2013-05-10 | 2013-05-11 | 2013-05-12 | 2013-05-13 | 2013-05-14 | 2013-05-15 | 2013-05-16 | 2013-05-17 | 2013-05-18 | 2013-05-19 | 2013-05-20 | 2013-05-21 | 2013-05-22 | 2013-05-23 | 2013-05-24 | 2013-05-25 | 2013-05-26 | 2013-05-27 | 2013-05-28 | 2013-05-29 | 2013-05-30 | 2013-05-31 | 2013-06-01 | 2013-06-02 | 2013-06-03 | 2013-06-04 | 2013-06-05 | 2013-06-06 | 2013-06-07 | 2013-06-08 | 2013-06-09 | 2013-06-10 | 2013-06-11 | 2013-06-12 | 2013-06-13 | 2013-06-14
VW - Gatepass control | [7 empty] | Initial | [5 empty] | Design |  | On Leave |  | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | Deepavali | UAT | UAT | UAT |  |  | UAT | UAT | UAT | Review UAT | Review UAT |  |  | Review UAT | Review UAT | GO/NO GO | [11 empty] | On Leave | On Leave | On Leave | On Leave | On Leave | [13 empty] | Christmas | [6 empty] | Year 2015 | [37 empty] | Chinese New Year | Chinese New Year | [44 empty] | Good Friday
BD - Case Label | Initial | Initial | [11 empty] | Design | Design |  | Design |  |  |  | Design | Design | Design | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev |  | Dev | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | Dev | Dev | Dev | Dev |  |  | Dev | UAT | UAT | UAT | UAT |  |  | UAT | UAT | UAT | UAT |  |  |  | UAT | UAT | Review UAT | Review UAT |  |  |  | Review UAT | Review UAT | Review UAT | Review UAT | Review UAT |  |  | GO/NO GO | Prepare System/Install | Prepare System/Install |  |  |  |  | Prepare System/Install | Go-Live | PILOT RUN | PILOT RUN | PILOT RUN | PILOT RUN
Initial | Work Shop
Design
Dev
UAT
Review UAT
GO/NO GO
Prepare System/Install
Go-Live
PILOT RUN
OFF DAY