## Task list
| Summary IT Requirement - |  |  |  |  | Updated 2016-05-17
S/N | Module | Function | Detail Description | Manday | By | Start Date | Estimated | Completed Date | SIT | STATUS | Remarks
1 | RF | RF Loading | 1. To have additional field to input "Tare weight", user to input after enter container #. Field is mandatory. 2. Remove "Whse" field in RF loading Screen, to set auto assign by user id. 3. To set warehouse code default by mapping to User login ID. If user ID is not setup in the list, user will not allow to perform loading. Codelkup listname = 'GHUSERID', ( utilised the same as guardhouse user codelist) | 2 | PF | 2016-05-19 | 2016-05-21 | 2016-05-20 | 2016-05-21 | Closed | Tested ok
2 | WMS | Import HU | Add new field, HU Weight from source file - allow update weight for existing HU | 1 | PF | 2016-05-19 | 2016-05-19 | 2016-05-19 | 2016-05-26 | Closed | Tested ok
3 | WMS | Gate pass | Gate pass shows the "Cargo Weight" , "Tare Weight" & "Total Gross Weight" Cargo weight = Total HU Weight Tare Weight = Container Tare weight Total Gross weight = Cargo weight + Tare weight | 1 | PF | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Closed | tare weight input field. Cargo weight get from detail. Gross weight = computed field
4 | WMS | Container Summary report | Summary report to have "Cargo Weight" , "Tare Weight" & "Total Gross Weight" | 1 | PF | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26 | Closed | Tested ok
5 | WMS | Loading Maintenance | Add new fields: Tare weight, Cargo weight (display) , gross weigth ( Display) | 1 | PF | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26 | Closed | Tested ok
6 | eTracker | etracker Listing | update container weights - tare weight , cargo weight and gross weight | 2 | PF & Yus | 2016-05-30 | 2016-05-31 |  |  |  | [2016.05.26] to raise separate ASR
7 | eTracker | Report | new detail container Report | 1 | PF & Yus | 2016-06-01 | 2016-06-01 |  |  |  | [2016.05.26] to raise separate ASR
8
9
9

## User list
| User ID | Site
T01 | vw.cmphang | TLC
T02 | vw.kklin | TLC
T03 | vw.dsalb | TLC
T04 | vw.phyee | TLC
T05 | vw.czbong | TLC
T06 | vw.pnala | TLC
T07 | vw.pasogar | TLC
S01 | vw.ksngin | SLC
S02 | vw.cktan1 | SLC
S03 | vw.lgunasala | SLC
S04 | vw.kkkerk | SLC
S05 | vw.skrisnan | SLC
S06 | vw.fwchoo | SLC
S07 | vw.alatif | SLC

## RF
Before changes: RF Loading Screen | Updated:
Added new field:
Ct. Tare Wgt (Container Tare weight)
Warehouse code setup as default by User id Login

## RF Loading
1. Scan HU
2. Enter Container #
3. Enter Container Tare Weight
System prompt if Tare weight is not enter.
Tare weight must be numeric input
4. Continue scan HU for loading.
List of loaded HU
5. once completed load, click [Save & Print DO]
Status updated to Loaded

## Import HU
WMS-> | Import HU to add HU weight data from source file.
1 | Added validation - weight must not be empty. HU will not be imported if Weight is empty
Imported result:

## Report
add Tare weight , Cargo weight and gross weight