## Summary
Date | 2016-06-17
Subject | System enhancement on Expiry control and capturing in WMS
Attendance | David GHLim | Pei Fong
Yeo
Cheng
Ai Chen
1. Master Expiry SKU import ( weekly) – Expiry SKU master based on SAP uploaded list P1
a. Add active Flag – set as Active when item is expiry , Set as in-active if item no longer expiry item.
b. If current sku not found in new SAP List,
i. Auto set in-active if SKU not in new SAP list but with scanning history,
ii. Auto delete SKU master if no scanning history.
c. Allow manual update active flag status,
d. Add audit history update.
2. RF capture – System to block scanning SKU not in Master Expiry SKU or SKU no longer expiry item. Include this scanning error in Daily Scan report.
3. Expiry Location maintenance – to capture for reporting purpose. No validation during scanning of expiry item.
4. Report – Weekly imported New SKU changes
5. Report – Normal item in Expiry location
6. Report – Expiry item not in expiry location
7. Report – Daily scanned report to include scanning error with remarks, “SKU not in master expiry” or “SKU no longer expiry item”.

## Timeline
Activity | Day | Target Date of Completion | Status | Remark
Requirement gathering- process mapping | 1 | 17th June | Closed
System Design | 1 | 22th Apr 2016 | Closed
System Development SIT | 12 | 27 Jun - 15 Jul 2016 | Open
System walkthrough |  | 2016-07-15 | Open | NA
User (UAT) Testing |  | 18 - 23 Jul 2016 | Open
System Review fine tuning (if Any) |  | 25-26 Jul 2016 | Open
Installation (RF/Application) |  | 27 - 30 Jul 2016 | Open
System Preparation Go-live | 1 | 1st Aug 2016 | Open
Target Go-Live |  | 1st Aug 2016 | Open

## Changes
IT Changes Task List
S/N | Module | Function | Detail Description | Priority (Phase) | Manday | By | Start Date | Target Date | Actual Completed date | SIT Result | STATUS | Remarks
1 | WMS | Master Expiry SKU | Weekly update SKU Expiry Master: - Admin require perform weekly update of SKU Expiry master list from SAP data. (Every Monday) Changes: 1. Add "Activeflag" a) Active = when part is expiry item b) inactive = when part is no longer expiry item c) When import from SAP file, for existing record in WMS: i) if SKU in SAP list will be set as "Active" ii) if SKU not in in SAP , further check in system case 1 - when SKU has scanning history, SKU will remain with status inactive case 2 - when SKU does not have any scanning history, Delete the sku master in WMS. - allow manual update the activeflag status ( by authorised user) 2. Keep track all the audit history , i.e . New SKU Upload status active flag. ( active, inactive or new ) , changes in Audit history report. 3. Add "SAP SKU" field. | 1 | 3 |  | 2016-06-24 | 2016-06-28 |  |  | OPEN
2 | RF | Capture Expiry | 1. Check scanned SKU, when SKU not found in master list: a. Prompt Error message: i. No longer Expiry Item ( when activeflag = inactive) ii. Not in master list b. reject the scanning, but insert as error scan. Capture Error messafe as remarks in scanning detail. 2. only allow manual add new master list, or amend the activeflag. | 1 | 2 |  | 2016-06-29 | 2016-07-01 |  |  | OPEN
3 | WMS | Expiry Location | New master location to upload expiry location from SAP system. ( propose Weekly upload) Purpose is to generate exipry location matching report with expiry sku and normal sku listing. - Do not require perform system validation during location scanning in RF capture. - Upload logic: 1. all location in SAP upload list, set location type as EXPIRY location. 2. Existing expiry location which is not found in SAP list , will be updated as non-expiry location. 3. keep track of history update. i.e ExpiryLoc , non-expiryLoc or New ExpiryLoc | 2 | 2 |  | 2016-07-07 | 2016-07-08
4 | Report | New Master Expiry upload changes list | List of Master upload changes weekly, to generate after each upload completed. Detail: SKU Current Status old status ABC Active In-Active BBB New CCC In-active Active | 1 | 2 |  | 2016-07-05 | 2016-07-06 |  |  | OPEN
5 | Report | Normal Item in Expiry Location | list of Normal SKU ( non-Expiry items) in Expiry location. - to check out in SAP inv Snapshot - auto email report together with daily inventory list | 2 | 1 |  | 2016-07-11 | 2016-07-11 |  |  | OPEN
6 | Report | Expiry Item NOT in Expiry Location | list of Expiry SKU not in Expiry location. - to check out in SAP inv Snapshot - auto email report together with daily inventory list | 2 | 1 |  | 2016-07-12 | 2016-07-12 |  |  | OPEN
7 | Report | Daily scan report | - to show remarks for those scanned error found - Remarks = "No longer Expiry item" or "Not in Master list" | 1 | 1 |  | 2016-07-04 | 2016-07-04 |  |  | OPEN
12