## Login
User ID
RF Application | Version 2.5.0 Build 2015.12.01

## Summary changes
Module | Objects | Changes
cus_sonymobile.pbl | dddw_std_orderfreq | Created new dropdown datawindow for order frequency
| d_sony_sku_crieteria. | Added Dropdown for order frequency
| d_skumaster_sony | Added Tab for order frequency
| u_x_std_maint_sku_sony | Added child reference and to insert data in SKU
SCHTS_SONY_RDC | Table - codelist | Added new code 'SMODRFRQ'
| dbo.codelkup | Added codes for 'SMODRFRQ' and changed description for 'ABC'

## SIT Test
WMS - Function: |  |  |  | Uat User login:
S/N | Category | Category Detail | Test scenario description | Expected Result | Tested by | Start Date | End Date | Result / remarks | Issue or change request | Reported date | Completed Date | Status
S-01 | SKU Master | Renaming ABC with changes in code Description | Changed codes should not be visible | New Modified code description should be visible
S-02 | SKU Master | New Field order freq with code 'SMODRFRQ' in database and in UI | Added code in codelist and codelkup would not be available | Order freq should be available with description codes
S-03 | SKU Master | New tab should be available in SKU screen | Tab would be available without values | Order freq tab should be available with its code values
|  |  | No. of Items in Test | 34
|  |  | No. of Items Test Pass | 29
|  |  | No. of Items Test Fail | 5
|  |  | No. of items test pass after Issues fixed | 34

## Screen
2- Order Frequency
3- Order freq Tab in SKU